## How to use
Multi-project tracker
Free template by Anas Abdullah · anasabdullah.dev
1. List every project once in the 'Projects' sheet (use a code like P1, P2 — no need for client names).
2. Add one row per task in the 'Tasks' sheet. Every task gets an owner, an expected outcome, and a status.
3. Fill in effort (rough hours), QA status, and the environment the work is currently in.
4. If a task is blocked, describe the blocker and choose whether it sits with the Client or the Team.
5. Use 'Linked tasks' (e.g. T-04, T-09) so related tasks can be updated together.
6. 'Projects' counts open tasks and blockers automatically. Check it every morning.
7. 'Timeline (Gantt)' draws a weekly bar for every task with a Start and Due date — no extra input needed.
Status values: To do · In progress · In review · QA · Blocked · Done
QA status values: Not started · Testing · Passed · Failed
Environments: Development · Staging · Pre-production · Production
Health (RAG): Green = on track · Amber = at risk · Red = off track
Definition of Done (edit per project): code reviewed · QA passed · deployed to staging · client accepted (UAT)
RAID log: record Risks, Assumptions, Issues and Dependencies per project, each with an owner and a next step.
Google Sheets: File → Import → Upload this file. Dropdowns and formulas carry over.
Read how this system works: https://anasabdullah.dev/writing/how-i-track-multiple-projects

## Tasks
Tasks
One row per task. Owner + outcome + status are required.
Task ID | Project | Task | Owner | Expected outcome | Status | Priority | Effort est. (h) | Effort actual (h) | Start | Due | QA status | Environment | Blocker | Blocker side | Linked tasks | Notes
T-01 | P1 | Set up staging environment | Dev A | Staging live and shared with QA | Done | High | 6 | 5 | 2026-11-02 | 2026-11-06 | Passed | Staging
T-02 | P1 | Login and sign-up screens | Dev B | Users can register and log in | QA | High | 16 | 18 | 2026-11-09 | 2026-11-20 | Testing | Staging |  |  | T-03
T-03 | P1 | Password reset flow | Dev B | Users can reset password by email | Blocked | Medium | 8 | 3 | 2026-11-16 | 2026-11-27 | Not started | Development | Waiting for email provider access | Client | T-02 | Requested in weekly meeting
T-04 | P2 | Payment integration | Dev C | Card payments work in sandbox | In progress | High | 20 | 12 | 2026-11-09 | 2026-12-04 | Not started | Development
T-05 | P2 | Admin reports | Dev D | Admins can export monthly reports | To do | Medium | 12 |  | 2026-12-07 | 2026-12-18 | Not started | Development |  |  | T-04

## Timeline (Gantt)
Timeline (Gantt)
Filled automatically from the Tasks sheet. Amber = planned or in progress · Red = blocked · Grey = done · Highlighted column = this week.
Timeline starts (Monday): |  |  | ← automatic (earliest task start); type a date to override
Task ID | Project | Task | Owner | Start | Due | Status

## Projects
Projects overview
Check this every morning: health, blockers, and when each client last heard from you.
Project | Name / description | Team size | Current phase / sprint | Next milestone | Milestone due | Health (RAG) | Open tasks | Blocked | Client-side blockers | Weekly client meeting | Last client update | Notes
P1 | Mobile app | 4 | Sprint 3 | Beta to client |  | Amber |  |  |  | Tuesday
P2 | Web dashboard | 3 | Sprint 1 | Payments live in staging |  | Green |  |  |  | Thursday

## RAID log
RAID log
Risks, Assumptions, Issues, Dependencies. Review weekly; every item needs an owner and a next step.
ID | Project | Type | Description | Impact | Likelihood | Owner | Next step | Due | Status
R-01 | P1 | Risk | Client feedback on designs may arrive late and delay the beta | High | Medium | PM | Agree feedback deadline in weekly meeting |  | Open
D-01 | P1 | Dependency | Email provider access needed for password reset | Medium | High | PM | Request access from client in writing |  | Open