## How to use
RACI matrix template
Free template by Anas Abdullah · anasabdullah.dev
1. In 'RACI matrix', list the roles across row 4 (use roles like 'Tech lead', not names, so the matrix survives team changes).
2. List the activities and decisions down column A. Focus on approvals, sign-offs, releases and changes.
3. Choose a letter in each cell from the dropdown. Leave a cell empty if the role isn't involved.
4. Give every row exactly one A (or A/R). Then add the R's, then only the C's and I's that are really needed.
5. The 'Check' column flags rows with no A, more than one A, or no R. Fix every row until it says OK.
6. 'Role summary' counts each role's A's and R's. Many A's and R's can mean a role is overloaded.
7. Review the matrix with the team and the client, then share it. Update it when the team or the phase changes.
R = Responsible: does the work. There can be more than one.
A = Accountable: owns the outcome and gives the final approval. Exactly one per row.
C = Consulted: gives input before or during the work (two-way).
I = Informed: kept up to date on progress or the result (one-way).
A/R = the same role is accountable and also does the work (common on small teams).
The example rows show a typical software client project. Replace them with your own.
Google Sheets: File → Import → Upload this file. Dropdowns and formulas carry over.
Read the full guide: https://anasabdullah.dev/writing/raci-matrix

## RACI matrix
RACI matrix
One A per row. Roles across, activities down. Choose letters from the dropdowns.
Activity / decision | Client | Project manager | Tech lead | Developers | QA | Designer | (role) | (role) | Check
Business requirements | A | R | C | I | I | C
User stories and acceptance criteria | C | A/R | C | C | C | C
UI/UX design | A | C | C | I | I | R
Estimates and timeline | C | A | R | C | C | C
Technical architecture | I | I | A/R | C | I | I
Development | I | I | A | R | C | C
Code review |  |  | A | R
QA testing | I | I | C | C | A/R
User acceptance testing (UAT) | A/R | R | I | I | C | I
Release approval | A | R | C | I | C | I
Deployment to production | I | I | A | R | C
Weekly status report | I | A/R | C | I | I | I
Change requests | A | R | C | I | I | C

## Role summary
Role summary
Calculated from 'RACI matrix'. Check overloaded roles and roles that may not need to be listed.
Role | A (incl. A/R) | R (incl. A/R) | C | I | Note