## How to use
Software estimation template
Free template by Anas Abdullah · anasabdullah.dev
1. In 'Estimate', break the work into deliverables and small tasks (a work breakdown structure). Split any task over a few days.
2. Include the work people forget: code review, QA and bug fixing, deployment, documentation, meetings. The example rows show them.
3. For each task, ask the person who will build it for three numbers in days: optimistic, most likely, pessimistic.
4. The sheet calculates the PERT estimate (O + 4M + P) ÷ 6 and a rough standard deviation (P − O) ÷ 6 for every task.
5. In 'Risks & buffers', list real unknowns with a visible buffer each. Mark a buffer 'Released' if the risk doesn't happen.
6. The summary at the top of 'Estimate' adds it all up and gives two numbers to share: ~84% and ~95% confidence.
7. Share a range with its assumptions and risks, not a single date. Re-estimate when you learn something new.
8. As work finishes, fill in 'Actual (days)'. 'Variance' shows which kinds of work you underestimate. Use it for the next estimate.
Notes
Effort is in person-days. Calendar weeks are a rough guide only: they ignore dependencies, holidays, and people working on other things.
Confidence levels assume tasks vary independently, a common simplification. Treat them as a guide, not a guarantee.
A red row means the three numbers aren't in order (optimistic ≤ most likely ≤ pessimistic).
The example rows show a small web project. Replace them with your own.
Google Sheets: File → Import → Upload this file. Dropdowns and formulas carry over.
Read the full guide: https://anasabdullah.dev/writing/estimating-software-work

## Estimate
Software estimate
Fill in the yellow cells and the task rows. Everything else is calculated.
Expected effort (sum of PERT estimates)
Standard deviation of the total (rough)
Risk buffers (not released)
Estimate to share, ~84% confidence (days)
Safer estimate, ~95% confidence (days)
People working in parallel |  | 2
Working days per week |  | 5
Rough calendar weeks (~84%)
Deliverable | Task | Optimistic (days) | Most likely (days) | Pessimistic (days) | PERT estimate (days) | Std dev (days) | Notes / assumptions | Actual (days) | Variance
Checkout | Cart summary screen | 1 | 2 | 4 |  |  | Design approved
Checkout | Payment provider integration | 3 | 5 | 15 |  |  | New provider for the team: see risk 1
Checkout | Order confirmation email | 0.5 | 1 | 2 |  |  | Email copy from the client
User accounts | Sign-up and login | 2 | 3 | 5
User accounts | Password reset | 1 | 1.5 | 3
Work people forget | Code review and fixes from review | 1 | 1.5 | 3
Work people forget | QA testing and bug fixing | 2 | 3 | 6
Work people forget | Deployment to staging and production | 0.5 | 1 | 2
Work people forget | Documentation and handover notes | 0.5 | 1 | 2
Work people forget | Meetings and client clarifications | 1 | 1.5 | 3

## Risks & buffers
Risks & buffers
One visible buffer per real risk. 'Released' buffers drop out of the estimate.
Risk / unknown | Affects task | Buffer (days) | Status | Plan (spike, question, decision)
Team hasn't used this payment provider before | Payment provider integration | 3 | Open | Run a 1-day spike first, then re-estimate
Email copy not final | Order confirmation email | 0.5 | Open | Ask the client for final copy this week