## Status report
WEEKLY PROJECT STATUS REPORT
Project | P1 — Mobile app |  |  | Report no. | 12
Client | Client A |  |  | Report date | 2026-11-20
Project manager | Your name |  |  | Period | 16 Nov – 20 Nov 2026
OVERALL STATUS
Amber |  | EXECUTIVE SUMMARY Login and sign-up are complete and in QA. Password reset is blocked on email provider access from the client. The beta stays on track if access is provided by Thursday.
→ Stable
HEALTH BY AREA
Area | Status | Trend | Comment
Scope | Green | → Stable | No changes to agreed scope this week.
Schedule | Amber | ↓ Declining | Password reset at risk until email access is provided.
Budget / effort | Green | → Stable | Effort within estimate (82 of 100 planned hours).
Quality | Green | ↑ Improving | QA running in parallel with development; no critical bugs open.
Resources | Green | → Stable | Team of 4, fully allocated.
KEY NUMBERS
% complete |  | Milestones on track |  | Open blockers |  | Open risks
62% |  | 3 of 4 |  | 1 |  | 2
MILESTONES
Milestone |  |  |  | Planned | Forecast | Status | Note
Staging environment ready |  |  |  | 2026-11-06 | 2026-11-06 | Green | Done
Login and sign-up in QA |  |  |  | 2026-11-20 | 2026-11-20 | Green
Beta release to client |  |  |  | 2026-11-27 | 2026-12-01 | Amber | Depends on email access
Payments live in staging |  |  |  | 2026-12-04 | 2026-12-04 | Green
PROGRESS
Completed this period |  |  |  | Planned next period
• Staging environment live and shared with QA • Login and sign-up built and moved to QA • Payment sandbox account set up |  |  |  | • Finish QA on login and sign-up • Start password reset once access is available • Continue payment integration
RISKS AND ISSUES
ID | Type | Description |  | Impact | Owner | Action / mitigation | Due
I-01 | Issue | Email provider access not yet provided |  | High | Client | Provide access or credentials | 2026-11-26
R-01 | Risk | Design feedback may arrive late for next sprint |  | Medium | PM | Agree feedback date in weekly call | 2026-11-24
DECISIONS NEEDED FROM CLIENT
Decision |  |  |  |  | Needed by | Owner | Impact if late
Confirm which email provider account to use for password reset |  |  |  |  | 2026-11-26 | Client | Beta slips
CHANGE REQUESTS
ID | Request |  |  |  | Effort | Timeline impact | Status
CR-01 | Add social login (Google) |  |  |  | 16 h | +3 days | Awaiting approval
Next meeting |  | Tuesday 24 Nov, 11:00 — weekly progress call
Free template by Anas Abdullah · anasabdullah.dev

## RAG guide
How to choose a status
Green | On track. No action needed from the client or management. Any risks are under control.
Amber | At risk. A deadline, budget, or quality target may be missed without action. State the action and who owns it.
Red | Off track. A target will be missed without a decision or extra help. Escalate in the same report, with options.
↑ Improving | Better than last week.
→ Stable | Same as last week.
↓ Declining | Worse than last week — explain why in the comment.

## How to use
Weekly project status report
Free template by Anas Abdullah · anasabdullah.dev
1. Duplicate the 'Status report' sheet each week (right-click the tab → Move or Copy → Create a copy). Keep old weeks as history.
2. Pick statuses from the dropdowns. Use the 'RAG guide' so everyone means the same thing by Green, Amber, and Red.
3. Write the executive summary last: what happened, what's at risk, and what you need — in 2–3 sentences.
4. Every risk, issue, and decision needs an owner and a date.
5. Send it in writing before the weekly meeting, then use the meeting for questions and decisions.
6. Print or export to PDF: the sheet is set up for one A4 page.
Google Sheets: File → Import → Upload this file. Dropdowns and colours carry over.
Read how this fits into a weekly project rhythm: https://anasabdullah.dev/writing/how-i-track-multiple-projects